## task_summary
Task Name | Task Status | Subtask Count | Rule Status | Estimated Hrs Remaining | Scope | Notes
Review Credit | completed | 8 | Complete | 0 | HELOC
Send Disclosures (HELOC) | completed | 14 | Complete | 0 | HELOC
Notice of Incomplete | completed | 3 | Partial | 4 | HELOC
Mailing Initial Disclosures | completed | 1 | Partial | 2 | HELOC
Order Appraisal | completed | 8 | Partial | 4 | HELOC
Order Title | completed | 4 | Partial | 2 | HELOC
Order Flood Certificate | completed | 1 | Complete | 0 | HELOC
ARM Disclosure | completed | 2 | Partial | 3 | RESI
Credit Score Disclosure | completed | 6 | Partial | 4 | HELOC
Withdraw Loan | completed | 3 | Partial | 4 | HELOC
Send Denial | completed | 4 | Partial | 6 | HELOC
File Closure Documents | completed | 5 | Partial | 2 | HELOC
Cancel Flood Certificate | completed | 1 | Partial | 2 | HELOC
Appraisal Refund | completed | 4 | Not Started | 3 | HELOC
Order SSA-89 | Partial | 0 | Not Started | 2 | HELOC
Order Tax Transcripts | Partial | 0 | Not Started | 4 | RESI
Order AVM | completed | 4 | Complete | 0 | HELOC
Flood Certificate Review | completed | 4 | Complete | 0 | HELOC
Order PAR | completed | 1 | Complete |  | HELOC
Recheck Flood | Partial | 0 | Partial | 1 | HELOC
Pre-Underwriting Checklist | completed | 11 |  |  | HELOC
Order HOI | completed | 1 | Partial | 2 | HELOC
HOI Review | completed | 13 | Partial | 8 | HELOC
Send Commitment Letter | completed | 3 | Partial | 2 | HELOC
Underwrite | completed | 4 | Partial | 8 | HELOC | Initial Undewrite path. Subsequent and Adverse paths need to be completed
Title (Ownership Report) | completed | 6 | Complete | 0 | HELOC
Review Appraisal | completed | 4 | Partial | 2 | HELOC | Needs testing/fine tuning
Send Appraisal | completed | 1 | Partial | 2 | HELOC | Initial Send Complete. Needs subsequent appraisal logic
Review Appraisal Second Review | completed | 2 | Partial | 3 | HELOC | Untested, recently developed.
Review Flood Insurance | planned | 0 | Planned | 8 | HELOC
Review PAR | completed | 4 |  |  | HELOC
Clear to Close | planned | 0 | Planned |  | HELOC
Master Property Insurance Review | completed | 14 |  |  | HELOC
Deny Loan | planned | 0 | Planned |  | HELOC
CounterOffer | planned | 0 | Planned |  | HELOC
Scheduling | planned | 0 | Planned |  | HELOC
Send Initial CD | planned | 0 | Planned |  | HELOC
Balance CD | planned | 0 | Planned |  | HELOC
Prepare Closing Package | planned | 0 | Planned |  | HELOC
Confirm Funding Figures | planned | 0 | Planned |  | HELOC
Approve Funding Figures | planned | 0 | Planned |  | HELOC
Fund Loan | planned | 0 | Planned |  | HELOC
Board Loan | planned | 0 | Planned |  | HELOC
Run UCD | planned | 0 | Planned |  | HELOC
Activate MERS | planned | 0 | Planned |  | HELOC
Activate MI | planned | 0 | Planned |  | HELOC
Credit Refresh | completed | 2 |  |  | HELOC
Fraud X Report | completed | 6 | Partial | 2 | HELOC | Needs testing/fine tuning
Deliver Note | planned | 2 |  |  | HELOC
Record Mortgage | planned | 0 |  |  | HELOC
Deliver Mortgage | planned | 2 |  |  | HELOC
Image Documents | planned | 0 |  |  | HELOC
eFolder Cleanup | planned | 0 |  |  | HELOC
Transfer to Cold Storage | planned | 0 |  |  | HELOC
Transfer to SaaS | planned | 0 |  |  | RESI
Initial Document Quality Assurance | completed | 29 | Complete | 0 | HELOC